## LOG
PROG280 Final Project Log
Task | Feature | Status | Duration | Description | Comments
Build a creative Gui | messaging between Server&Client | Started | longer than necessary |  | Cant think this through
Understand how the communication works | send file to the service | completed | 3hrs |  | dead tired
Client should get a list of files from Server | using a custom Class to facilitate the name of a file and byte[] to store bytes | finally achieved | 5hrs |  | how can someone love coding?
!list and !get | request from the client to get a list of files the server has or a specific file from the server | completed | 5hrs |  | I am finally understanding this
thinking about a game to be shared over the connection | multiplayer | not started | too long |  | scary
User and Host accounts | login accounts | completed | 4hrs |  | tired but feeling better
wire up buttons | communication done using database sql | almost done |  |  | small achievements
connection issues!!!!! | cant figure this out | stuck | 6hrs |  | stuck!!!!!!!
restart project | not doing a game again |  | 1hr |  | time is running out
designed other forms as windows for the client | welcome form meeting form etc | 1hr |  |  | late nights on this
finally somethings working

## EXAMPLE
PROG280 Final Project Log - EXAMPLE
Task | Feature | Status | Duration | Description | Comments
Implement transparent image support | Chat | Completed | 30 minutes | Wasn't that hard I found an example on codeproject | 10/10 would not do this again
Add emoji support | Chat | Abandonned | 5 hours | No one even likes emojis | This is a debatable topic but I decided to scrap the feature
Additional TCP connection for sharing screen image | Meeting | In-Progress | ~1 hour so far | An additional connection will be created so the images do not disrupt the chat functionality | Works okay but UDP may have alleviated bandwidth issues
Request control | Remote Control | Not-Started |  | Allow a user to request control from the host PC | Struggling on where to begin this task